## Ranking user stories
Ranking and selection of user stories for agile implementation
Selected | Story | Risk | BizValue | Hours
1 | Tweety | 3 | 4 | 4
1 | Huey | 5 | 2 | 5
1 | Buzz | 2 | 6 | 7
1 | Tom | 7 | 1 | 2
1 | Sylvester | 3 | 9 | 7
1 | Daffy | 1 | 4 | 6
1 | Jerry | 4 | 7 | 8
1 | Woody | 5 | 2 | 4
1 | Dewey | 2 | 8 | 9
1 | Mickey | 6 | 3 | 4
1 | Bugs | 3 | 5 | 6
1 | Lady | 5 | 2 | 3
1 | Louie | 2 | 7 | 5
1 | Tramp | 7 | 4 | 6
1 | Donald | 8 | 8 | 8
| Totals | 63 | 72 | 84
Iteration | 40
Value | 72 | total business value of all selected user stories
Duration | 84 | total number of hours to implement all user stories
Together | 0 | Huey, Dewey, and Louie can only be taken together
Apart | 1 | Sylvester and Tweety cannot be taken together