## The Problem
Linear Programming ranking of portfolio of projects with two constraints:
First: overall constraint on budget
Second: overall constraint on number of personnel
What is the selection of projects that maximizes NPV but stays within overall budget and personnel constraints?
| Project | Persons | Cost | NPV
| A | 3 | 100 | 135
| B | 2 | 60 | 90
| C | 4 | 90 | 130
| D | 2 | 50 | 70
| E | 5 | 200 | 270
| F | 3 | 110 | 150
| G | 4 | 90 | 100
| H | 6 | 250 | 350
| I | 3 | 60 | 100
| J | 2 | 55 | 80
| Totals | 34 | 1065 | 1475
Budget | 500 | the total budget available for all selected projects
Personnel | 15 | the total personnel available for all selected projects

## The Solution
Linear Programming solution
Selected | Project | Persons | Cost | NPV
1 | A | 3 | 100 | 135
1 | B | 2 | 60 | 90
1 | C | 4 | 90 | 130
1 | D | 2 | 50 | 70
1 | E | 5 | 200 | 270
1 | F | 3 | 110 | 150
1 | G | 4 | 90 | 100
1 | H | 6 | 250 | 350
1 | I | 3 | 60 | 100
1 | J | 2 | 55 | 80
| Totals | 34 | 1065 | 1475
Budget | 500 | the total budget available for all selected projects
Personnel | 15 | the total personnel available for all selected projects
Costs | 1065 | the actual costs sum of costs of selected projects
Manpower | 34 | the actual manpower used sum of persons of selected projects
Value | 1475 | the total value (NPV) of all selected projects, to maximize